## Notes
GGB
REC
CEM
Fire
Police
Need Picture
HGY
1. The <Data> tab is protected. The password to unlock it is "password"
2. Discuss the definition of expenditure year with the group. Suggested wording "Expenditure Year is meant to indicate the year when the bulk of the spending will occur or will begin to occur if the project spans multiple years. Pre-work (design, engineering, legal and permitting) may need to be broken out separately.
3. Added categories for "Estimated Life". Could do the same with estimated cost, but not sure that is best route to go. Discuss with group. Categories designed to track with likely bond or financing terms.
4. Renamed the project in tab 45 to be more descriptive and easier to tell the difference from 16 (transfer station - full)
Notes from 9/17/2024 - rich to consolidate all pool buildings into "pool complex" in tab 5 . Tabs 7, 8&9 were deleted.
check spelling on cemetary
cemetary has expendable trust fund. no capital reserve.
10/8/2024 - True up edit dates and 5 ton comments.
10/29/2024 - redistribute slide 10 to individual rec projects
8/26/2025 - Remove "terrible idea" and add "Highway Department" to tab
9/9/2025 - create new tab for new fire truck (43)
9/9/2025 - transfer station bond - keep retire non bond options
9/28/2025 - Created new Capital Reserve Fund "Inactive". This will let us filter out projects that are not currently under consideration (1973 Grader for example)

## Drop Down Values
Department | Funding Sources | Project Type | Project Status | Estimated Life | Captial Reserve Funds
Administration | Budget or Warrant Article | New | Recommend | 5 years or less | Distressed Buildings
Assessing | Reserve Fund | Repair/Upgrade | Defer Short Term | 6-10 years | Highway Equipment
Building | State or Federal Grant | Replacement | Defer Long Term | 11-25 years | Pool/Rec Facilities
Cemetery | Bond Issue |  | Not Recommended | 25+ years | Assessing
Code Enforcement |  |  | No Recommendation |  | Prospect Street Dump
Direct Assistance |  |  |  |  | Road Maintenance
Elections & Voting |  |  |  |  | Solid Waste Disposal
Fire, EMS & Police |  |  |  |  | Tech/Computer
General Govt Buildings |  |  |  |  | Town Building Maintenance
Health Officer |  |  |  |  | Police Cruiser
Library |  |  |  |  | Police Equipment
Planning & Zoning Board |  |  |  |  | Ambulance
Police |  |  |  |  | Fire Truck
Public Works |  |  |  |  | Fire Dept Emergency Safety Equipment
Recreation |  |  |  |  | Library
Tax Collector |  |  |  |  | Cemetary
Town Clerk |  |  |  |  | Public Safety Building
Highway |  |  |  |  | Inactive

## Data
Key | Date Added | Last Edited | Project Title | Department | Project Type | Committee Assessment | Expenditure Year | Estimated Life | Estimated Cost | Base Year | Likely Funding Source | CRF Account | Estimated Inflation Rate | Project Description | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030
1 | 2024-09-03 | 2025-08-26 | Library Building Capital Reserve | Library | Repair/Upgrade | No Recommendation | 2026 | 5 years or less | 0 | 2025 | Budget or Warrant Article | Library | 5% | 8/26/2025 - SB does not control capital projects Prior Year Notes: Discuss deferring capital fund request and allocating elsewhere (transfer station). Budget year 2025. | 0 | 0 | 0 | 0 | 0 | 0
2 | 2024-09-03 | 2025-08-26 | Visitors Center - Ongoing Maintenance | General Govt Buildings | Repair/Upgrade | Defer Short Term | 2026 | 5 years or less | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | 8/26/2025 - No new projects >$25k for coming year. Fund GGB reserve recognizing that there will be future repairs and maintenence required. Prior Year Notes: Repairs to roof were approved and allocated for 2025. However, there is likely additional foundation and drainage work to be done. Increase GGB capital reserve ask to $30k (from $20k) for additional repairs in near future? What is the Town's goal for this building? | 0 | 0 | 0 | 0 | 0 | 0
3 | 2024-09-03 | 2025-08-26 | Town Hall - Engineering Study for Stair Repair | General Govt Buildings | Repair/Upgrade | Recommend | 2025 | 25+ years | 25000 | 2025 | Reserve Fund | Town Building Maintenance | 5% | 8/26/2025 - Need engineering report (water remediation). Study would cost ~ $25k. Hope to roll actual repairs into Public Safety Bldg. Prior Year Notes: Front granite steps securing railing and reparing broken/chipped granite. Stabilize stairs. Estimated cost is a suggested ask for GGB capital reserve fund - - warrant article. Increase GGB capital reserve ask by $10k to offset future cost of repairing steps. Working on finding a mason/contractor to look at project. | 0 | 25000 | 0 | 0 | 0 | 0
4 | 2024-08-20 | 2025-08-26 | Highway Garage - unheated addition for equipment storage | General Govt Buildings | Repair/Upgrade | Defer Short Term | 2026 | 25+ years | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | 8/26/2025 - Project mentioned but undefined. When would he like built? | 0 | 0 | 0 | 0 | 0 | 0
5 | 2024-08-20 | 2025-08-26 | Swimming Pool | Recreation | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Pool/Rec Facilities | 5% | 8/26/2025 - Concrete pad has been repaired and roofs replaced in recent memory. No projects identified for 2026 - continue building reserve. | 0 | 0 | 0 | 0 | 0 | 0
6 | 2024-08-20 | 2025-08-26 | Pool Complex | Recreation | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Pool/Rec Facilities | 5% | 8/26/2025 - Concrete pad has been repaired and roofs replaced in recent memory. No projects identified for 2026 - continue building reserve. | 0 | 0 | 0 | 0 | 0 | 0
10 | 2024-08-20 | 2025-08-26 | Other Rec. Properties - Snack Shack | Recreation | Repair/Upgrade | Recommend | 2025 | 25+ years | 5000 | 2025 | Reserve Fund | Pool/Rec Facilities | 5% | 8/26/2025 - Snack Shack upgrade/replacement - placholder value $40k. Prior year comments Tennis Courts, Basketball Courts, Ball fields, Playground, Future Skate Park and Gazebo. Snack shack replacement Fencing (Basketball and ball fields) - use money in revolving or 10 fund Landscaping playground. | 0 | 40000 | 0 | 0 | 0 | 0
11 | 2024-08-20 | 2025-08-26 | Gazebo | Recreation | Repair/Upgrade | No Recommendation | 2025 | 25+ years | 2500 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | 8/26/2025 - No expenditures for 2026 Prior Year Notes: Add $2,500 to reserve for future repairs and maintenance. | 0 | 0 | 0 | 0 | 0 | 0
12 | 2024-08-20 | 2025-08-26 | Utility Building | Cemetery | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | 8/26/2025 - MAY have a 2026 project. MM will check with Trustees. Placeholder - Request budget info from cemetery committee. They have their own trust. | 0 | 0 | 0 | 0 | 0 | 0
13 | 2024-08-20 | 2025-08-26 | Elm Street Ball Park | Recreation | Repair/Upgrade | Defer Long Term | 2027 | 25+ years | 100000 | 2025 | Reserve Fund | Pool/Rec Facilities | 5% | Abby is requesting quotes for fencing project. Funding needs to be planned and will likely require some non-taxpayer money. Resizing of fields is due to be complete Fall 2025. Paid out of rec budget. | 0 | 0 | 0 | 0 | 0 | 0
14 | 2024-08-20 | 2025-08-26 | Basketball Court | Recreation | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | Placeholder. | 0 | 0 | 0 | 0 | 0 | 0
15 | 2024-08-20 | 2025-08-26 | Tennis Court | Recreation | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Pool/Rec Facilities | 5% | 8/26/2025 - Cracking at base of net posts will need to be repaired. Ongoing maintenance/resurfacing. | 0 | 0 | 0 | 0 | 0 | 0
16 | 2024-09-03 | 2025-08-26 | Future Transfer Station - Full | General Govt Buildings | New | Recommend | 2026 | 25+ years | 1000000 | 2025 | State or Federal Grant | Town Building Maintenance | 5% | This option assumes a fully built transfer station using Aries Engineering design. - Congressional Discretionary Spending submitted by Senator Sheehan - EPA grant | 0 | 0 | 1000000 | 0 | 0 | 0
17 | 2024-09-03 | 2025-08-26 | Future Public Safety Building | Fire, EMS & Police | New | Defer Short Term | 2028 | 25+ years | 5000000 | 2025 | Bond Issue | Town Building Maintenance | 5% | 8/26/2025 - Engineering study is the next step - would come out of exisiting capital reserve. Very preliminary estimate. - No site selected - No engineering plans | 0 | 0 | 0 | 0 | 0 | 0
18 | 2024-08-20 | 2025-09-09 | Solar Array | General Govt Buildings | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | 9/9/2025 Need warranty info from energy commission. 30 year life expectancy. Capital expenditures >$25k are unlikely. Maintenance (ballast failure) will be the first likely need at year 10. No need to make specific request to GGB this year. | 0 | 0 | 0 | 0 | 0 | 0
19 | 2024-08-20 | 2025-09-09 | Prospect Street Building | General Govt Buildings | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | 9/9/2025 Possible outdoor storage project in 2025 or 2026. See tab 4. Highway Department - needs new HVAC - - new boiler -- both are original to the building. Big Ass Fan (BAF) with a vent. Windows have been replaced. | 0 | 0 | 0 | 0 | 0 | 0
20 | 2024-08-20 | 2025-09-09 | TA3500 - Trailer | Fire & Rescue | Replacement | Defer Short Term | No Planned Expenditure | 25+ years | 2900 | 2025 | Budget or Warrant Article | Inactive | 5% | 9/9/2025 - Storage for Fire Department in parking lot. Will likely get more use when FD gets utility truck. Unlikely that Town would replace this for $25k, delete or retire this tab. | 0 | 0 | 0 | 0 | 0 | 0
21 | 2024-08-20 | 2025-09-09 | 2020 Explorer (Cruiser 2) | Police | Replacement | Defer Short Term | 2026 | 5 years or less | 0 | 2029 | Reserve Fund | Police Cruiser | 5% | 9/9/2025 - Replacement cycle is slowing because the Department has been understaffed (3 years). This replacement may shift to 2027. Mary will check with Chief. 9/28/2025 - This replacement may shift to 2027. Hybrid may need to be replaced before the 2019 it will depend on which is worse at the end of year. Ideally this will be replaced 2029 Annual request from $25,000 to $35,000. | 0 | 0 | 0 | 0 | 0 | 0
22 | 2024-08-20 | 2025-09-09 | 2023 Charger (Cruiser 1) | Police | Replacement | Defer Short Term | 2029 | 5 years or less | 0 | 2029 | Budget or Warrant Article | Police Cruiser | 5% | See tabs 21 and 23. Life cycle is longer than patrol vehicles and will be the last to be replaced. | 0 | 0 | 0 | 0 | 0 | 0
23 | 2024-08-20 | 2025-09-09 | 2019 Explorer (Cruiser 4) | Police | Replacement | Defer Short Term | 2027 | 5 years or less | 0 | 2026 | Budget or Warrant Article | Police Cruiser | 5% | See tabs 21 and 23. Likely need to increase capital reserve or use unallocated fund balance and warrant article. | 0 | 0 | 0 | 0 | 0 | 0
24 | 2024-08-20 | 2025-09-09 | 2025 Explorer (Cruiser 3) | Police | Replacement | Defer Short Term | 2031 | 5 years or less | 70000 | 2031 | Budget or Warrant Article | Police Cruiser | 5% | See previous cruiser tabs | 0 | 0 | 0 | 0 | 0 | 0
25 | 2024-08-20 | 2025-09-09 | 2017 FT581 Trailer | Police | Replacement | Defer Short Term | 2025 | 25+ years | 3500 | 2025 | Budget or Warrant Article | Inactive | 5% | Located at 116 site. Storage for police training materials. May be retired and reused at future transfer station. Not likely to be replaced. CONSIDER DELETING or RETIRING THIS TAB. | 0 | 0 | 0 | 0 | 0 | 0
26 | 2024-08-20 | 2025-09-09 | 2020 M2 106 (Dump Truck John ) - 5 Ton | Highway | Replacement | Defer Short Term | 2035 | 11-25 years | 300000 | 2035 | Reserve Fund | Highway Equipment | 5% | 9/9/2025 Continue adding to capital reserve $50k. This can also be replaced using revolving funds. | 0 | 0 | 0 | 0 | 0 | 0
27 | 2024-08-20 | 2024-10-08 | 2019 Ram 1500 Pickup (tradeable) | Highway | Replacement | Defer Short Term | 2026 | 5 years or less | 70000 | 2025 | Budget or Warrant Article | Highway Equipment | 5% | Possible move to transfer station. | 0 | 0 | 0 | 0 | 0 | 0
28 | 2024-08-20 | 2025-09-09 | 2016 F350 - 1 Ton (from Water Dept.) | Highway | Replacement | Defer Short Term | 2025 | 5 years or less | 100000 | 2025 | Reserve Fund | Highway Equipment | 5% | 9/9/2025 This truck may or may not be replaced. FD got the last Water Department hand me down truck. 9/11/2025 Brett: Not a must have and if it is replaced it would be 5 years from now. It does get used but depending on circumstances will determine if it's replaced. | 0 | 0 | 0 | 0 | 0 | 0
29 | 2024-08-20 | 2025-09-09 | 2018 Dump Truck - 5 Ton (Chris) | Highway | Replacement | Defer Short Term | 2033 | 6-10 years | 300000 | 2025 | Budget or Warrant Article | Highway Equipment | 5% | 8/9/2025 - Need to look at large truck purchases coming up and compare to reserve and revolving fund. | 0 | 0 | 0 | 0 | 0 | 0
30 | 2024-08-20 | 2025-09-09 | 2015 Loader 420 F2 IT (backhoe) | Highway | Replacement | Defer Short Term | 2030 | 11-25 years | 101000 | 2025 | Budget or Warrant Article | Highway Equipment | 5% | 9/9/2025 - Review against capital plan and revolving fund. | 0 | 0 | 0 | 0 | 0 | 0
31 | 2024-08-20 | 2025-09-09 | 2011 Dump Truck (Brett) - 5 Ton | Highway | Replacement | Defer Short Term | 2026 | 25+ years | 300000 | 2025 | Reserve Fund | Highway Equipment | 5% | 9/9/2025 - This replacement year will probably push out a few. | 0 | 0 | 0 | 0 | 0 | 0
32 | 2024-08-20 | 2025-09-09 | 2009 Dump Truck (Rick) - 5 Ton | Highway | Replacement | Defer Short Term | 2025 | 11-25 years | 241041 | 2025 | Reserve Fund | Highway Equipment | 5% | 9/9/2025 - Being replaced in 2025 - ordered and paid for (funded) 09/28/2025 submitting a grant opportunity to pay $250,000 of the $300,000. Truck is slated to be ready January 2026 | 0 | 0 | 0 | 0 | 0 | 0
33 | 2024-08-20 | 2024-10-08 | 1973 Grader | Highway | Replacement | Defer Short Term | No Planned Expenditure | 25+ years | 0 | 2025 | Budget or Warrant Article | Inactive | 5% | 9/9/2025 Very expensive to replace. Currently grade 8 miles of road in Town. This will be dealt with when the inevitable happens. No need to plan for a replacement. | 0 | 0 | 0 | 0 | 0 | 0
34 | 2024-08-20 | 2025-09-09 | 1085D - Heavy Equipment | Highway | Replacement | Defer Short Term | 2039 | 11-25 years | 300000 | 2025 | Budget or Warrant Article | Highway Equipment | 5% | 9/9/2025 - No need to plan for replacement at this time - - 2039 replacement year | 0 | 0 | 0 | 0 | 0 | 0
35 | 2024-08-20 | 2025-09-09 | 2023 Ram 5500 1 Ton | Highway | Replacement | Defer Short Term | 2033 | 6-10 years | 100000 | 2025 | Reserve Fund | Highway Equipment | 5% | 9/9/2025 - Replacement is far in the future. | 0 | 0 | 0 | 0 | 0 | 0
36 | 2024-08-20 | 2025-09-09 | 2020 926M (Loader) | Highway | Replacement | Defer Short Term | 2035 | 11-25 years | 150000 | 2025 | Reserve Fund | Highway Equipment | 5% | 9/11/2025 12-15 year lifespan Brett explained rust drives replacement timing | 0 | 0 | 0 | 0 | 0 | 0
37 | 2024-08-20 | 2025-08-05 | 2016 MSVII Ambulance | Fire & Rescue | Replacement | Defer Short Term | 2028 | 6-10 years | 400000 | 2025 | Reserve Fund | Ambulance | 5% | $125,000 ambulance reserve 9/11/2025 Met with John and a new ambulance is going to cost roughly $400,000 and 2 years once ordered. Creating a revolving fund 2026 town meeting but will need to fund $250,000 possibily 4 years. 8/5/2025 - Reserve ask will be influenced by whether or not ambulance revolving fund is approved by taxpayers. Ambulance services generate $60k per year. Currently, this money goes into General Fund. Payrolls goes through General fund. Ask for $25k for reserve and project $35k to revolving fund in 2026. | 0 | 0 | 0 | 0 | 0 | 0
38 | 2024-08-20 | 2025-09-09 | 2004 Fire Truck | Fire & Rescue | Replacement | Defer Short Term | No Planned Expenditure | 25+ years | 0 | 2025 | Reserve Fund | Inactive | 5% | 9/9/2025 - This truck will be SOLD. Capital Reserve and ARPA funds. Replacemet is on back order. Fully funded! 9/11/2025 John is working on selling this trck and proceeds should go to the capital reserve | 0 | 0 | 0 | 0 | 0 | 0
39 | 2024-08-20 | 2025-09-09 | 2000 FL-80 - Pumper | Fire & Rescue | Replacement | Defer Short Term | 2027 | 25+ years | 1000000 | 2025 | Budget or Warrant Article | Fire Truck | 5% | 9/9/2025 24 year old truck. We have 1 brand new truck coming in 2025. May or may not need to be replaced when it fails. Remaining life is short. Replacement if it happens will need to be paid for with a bond issue. Insurance upto 20 years covers the actual truck after 20 yrs it's the value of the truck 8/5/2025 - Fire Chief believes that truck should be replaced. Timing TBD. | 0 | 0 | 0 | 0 | 0 | 0
40 | 2024-08-20 | 2025-09-09 | 1998 Tanker | Fire & Rescue | Replacement | Defer Short Term | 2034 | 25+ years | 500000 | 2025 | Reserve Fund | Fire Truck | 5% | 9/9/2025 May be an opportunity to fund with grants. | 0 | 0 | 0 | 0 | 0 | 0
41 | 2024-08-20 | 2025-09-09 | 1977 F150 Brush Truck | Fire & Rescue | Replacement | Defer Short Term | No Planned Expenditure | 25+ years | 0 | 2025 | Budget or Warrant Article | Inactive | 5% | Not going to be replaced. RETIRE THIS TAB | 0 | 0 | 0 | 0 | 0 | 0
42 | 2024-08-20 | 2025-09-09 | 1948 Fire Truck | Fire & Rescue | Replacement | Defer Short Term | No Planned Expenditure | 25+ years | 0 | 2025 | Budget or Warrant Article | Inactive | 5% | Not being replaced. RETIRE THIS TAB | 0 | 0 | 0 | 0 | 0 | 0
43 | 2024-08-20 | 2024-08-20 | 2025 New Fire Truck | Fire & Rescue | Replacement | Defer Short Term | 2045 | 25+ years | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | Replacement for the other truck. | 0 | 0 | 0 | 0 | 0 | 0
44 | 2024-08-20 | 2024-08-20 | Prospect Street Bridge | Highway | Replacement | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Budget or Warrant Article | Town Building Maintenance | 5% | Placeholder. | 0 | 0 | 0 | 0 | 0 | 0
45 |  |  | Future Transfer Station - Full (bond) | General Govt Buildings | New | Recommend | 2026 | 25+ years | 750000 | 2025 | Bond Issue | Town Building Maintenance | 5% | This option assumes a fully built transfer station using Aries Engineering design. Difference is that Town would use existing capital reserve, minor grants and then borrow the remaining balance. | 0 | 0 | 0 | 0 | 0 | 0
46 |  |  | Future Transfer Station - Phase 1 | General Govt Buildings | New | Recommend | 2026 | 25+ years | 300000 | 2025 | Reserve Fund | Town Building Maintenance | 5% | Phase 1 using only Town resources (capital reserve fund, minor local grants). | 0 | 0 | 0 | 0 | 0 | 0
47 |  |  | Town Hall - Other upgrades and repairs | General Govt Buildings | Repair/Upgrade | Defer Short Term | 2025 | 25+ years | 0 | 2025 | Reserve Fund | Town Building Maintenance | 5% | Front Door replaced, double hung windows replaced or repaired, non-functioning interior doors, re-point mortar. Some of appropriation could come out of general building maintenance line item. | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Date Added = VLOOKUP(B1,INDIRECT([Key]&"!$B4:J55"),4,FALSE)

## CRF Balances
Capital Reserve/Special Warrant | Current Balance | 2025 Approved | 2026 Proposed | $ Change | Comments
Road Maintenance Capital Reserve | 22000 | 0 | 70000 | 70000
Highway Equipment | 173246 | 50000 | 50000 | 0 | Lowered due to grant $192,000
Fire Emerg. Safety Equip | 7305 | 10000 | 35000 | 25000
Fire Truck | 34051 | 30000 | 50000 | 20000
Concerts |  | 9650 | 12000 | 2350
Police Cruiser | 54524 | 35000 | 35000 | 0
Ambulance | 126159 | 25000 | 25000 | 0
Library Capital Reserve Fund | 96647 | 15000 | 15000 | 0
Police Equipment | 15451 | 5000 | 5000 | 0
New Public Safety Facility | 103855 | 0 | 0 | 0
Grant Match Expendable Trust | 20043 | 0 | 30000 | 30000 | First to be removed if a reduction is required
Rec/Pool Facility | 34294 | 27500 | 25000 | -2500
Computer | 27379 | 8000 | 5000 | -3000
Town Building Maintenance | 109026 | 40000 | 30000 | -10000
Cemetery Trust | 45883 | 25000 | 10000 | -15000
Assessing | 15049 | 26000 | 5000 | -21000
Solid Waste | 321091 | 40000 | 0 | -40000
| Total: | 346150 | 402000 | 55850
Note on C2: Richard Southwell: Use September 30,2025 or just before presentation to Select Board.

## Pivot
Department | Police
CRF Account | Police Cruiser
Row Labels | Sum of Estimated Cost
2026 | 0
2020 Explorer (Cruiser 2) | 0
2027 | 0
2019 Explorer (Cruiser 4) | 0
2029 | 0
2023 Charger (Cruiser 1) | 0
2031 | 70000
2025 Explorer (Cruiser 3) | 70000
Grand Total | 70000

## Police Cruiser
Department | Police
CRF Account | Police Cruiser
Row Labels | Sum of Estimated Cost
2026 | 0
2020 Explorer (Cruiser 2) | 0
2027 | 0
2019 Explorer (Cruiser 4) | 0
2029 | 0
2023 Charger (Cruiser 1) | 0
2031 | 70000
2025 Explorer (Cruiser 3) | 70000
Grand Total | 70000
Opening Capital Reserve Fund Balance | 173246
Newly delivered cruiser | 0
173246
2026 Capital Reserve Fund Request | 35000
New Balance 2026 | 208246

## Highway Pivot
Department | Highway
CRF Account | Highway Equipment
Row Labels | Sum of Estimated Cost
2025 | 341041
2009 Dump Truck (Rick) - 5 Ton | 241041
2016 F350 - 1 Ton (from Water Dept.) | 100000
2026 | 370000
2011 Dump Truck (Brett) - 5 Ton | 300000
2019 Ram 1500 Pickup (tradeable) | 70000
2030 | 101000
2015 Loader 420 F2 IT (backhoe) | 101000
Grand Total | 812041
Opening Capital Reserve Fund Balance | 22000
Opening Highway Resoving Fund Balance | 274000
296000
2009 Dump Truck (Rick) - 5 Ton | -241041
54959
2026 Capital Reserve Fund Request | 75000
2026 Highway Revolving Fund Allocation (est) | 100000
New Balance 2026 | 229959

## Fire Pivot
Department | Fire & Rescue
CRF Account | Fire Truck
Row Labels | Sum of Estimated Cost
2027 | 1000000 | Lets talk about the expenditure year
2000 FL-80 - Pumper | 1000000
Grand Total | 1000000
Opening Capital Reserve Fund Balance | 0
Newly delivered fire truck | -475000
-475000
2026 Capital Reserve Fund Request | 50000
New Balance 2026 | -425000

## Ambulance Pivot
Department | Fire & Rescue
CRF Account | Ambulance
Row Labels | Sum of Estimated Cost
2028 | 400000 | Lets talk about the expenditure year
2016 MSVII Ambulance | 400000
Grand Total | 400000
Opening Capital Reserve Fund Balance | 54524
Opening Highway Resoving Fund Balance | 0
54524
2026 Capital Reserve Fund Request | 25000
2026 Projected Revolving Fund | 35000
New Balance 2026 | 114524

## Recreation
Department | Recreation
Row Labels | Sum of Estimated Cost
2025 | 7500
Pool/Rec Facilities | 5000
Pool Complex | 0
Swimming Pool | 0
Tennis Court | 0
Other Rec. Properties - Snack Shack | 5000
Town Building Maintenance | 2500
Basketball Court | 0
Gazebo | 2500
2027 | 100000
Pool/Rec Facilities | 100000
Elm Street Ball Park | 100000
Grand Total | 107500

## Fire, EMS & Police Pivot
Department | Fire, EMS & Police
Row Labels | Sum of Estimated Cost
2028 | 5000000
Town Building Maintenance | 5000000
Future Public Safety Building | 5000000
Grand Total | 5000000

## 1
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2025-08-26
Project Title |  | Library Building Capital Reserve
Department |  | Library
Project Type |  | Repair/Upgrade
Committee Assessment |  | No Recommendation
Expenditure Year |  | 2026
Estimated Life |  | 5 years or less
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Library
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - SB does not control capital projects Prior Year Notes: Discuss deferring capital fund request and allocating elsewhere (transfer station). Budget year 2025.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 2
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2025-08-26
Project Title |  | Visitors Center - Ongoing Maintenance
Department |  | General Govt Buildings
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2026
Estimated Life |  | 5 years or less | 5
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - No new projects >$25k for coming year. Fund GGB reserve recognizing that there will be future repairs and maintenence required. Prior Year Notes: Repairs to roof were approved and allocated for 2025. However, there is likely additional foundation and drainage work to be done. Increase GGB capital reserve ask to $30k (from $20k) for additional repairs in near future? What is the Town's goal for this building?
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 3
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2025-08-26
Project Title |  | Town Hall - Engineering Study for Stair Repair
Department |  | General Govt Buildings
Project Type |  | Repair/Upgrade
Committee Assessment |  | Recommend
Expenditure Year |  | 2025
Estimated Life |  | 25+ years | 30
Estimated Cost |  | 25000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - Need engineering report (water remediation). Study would cost ~ $25k. Hope to roll actual repairs into Public Safety Bldg. Prior Year Notes: Front granite steps securing railing and reparing broken/chipped granite. Stabilize stairs. Estimated cost is a suggested ask for GGB capital reserve fund - - warrant article. Increase GGB capital reserve ask by $10k to offset future cost of repairing steps. Working on finding a mason/contractor to look at project.
| Year | Funding
| FY2025 | 0
| FY2026 | 25000
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 4
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Highway Garage - unheated addition for equipment storage
Department |  | General Govt Buildings
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2026
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - Project mentioned but undefined. When would he like built?
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 5
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Swimming Pool
Department |  | Recreation
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Pool/Rec Facilities
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - Concrete pad has been repaired and roofs replaced in recent memory. No projects identified for 2026 - continue building reserve.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 6
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Pool Complex
Department |  | Recreation
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Pool/Rec Facilities
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - Concrete pad has been repaired and roofs replaced in recent memory. No projects identified for 2026 - continue building reserve.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 10
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Other Rec. Properties - Snack Shack
Department |  | Recreation
Project Type |  | Repair/Upgrade
Committee Assessment |  | Recommend
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 5000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Pool/Rec Facilities
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - Snack Shack upgrade/replacement - placholder value $40k. Prior year comments Tennis Courts, Basketball Courts, Ball fields, Playground, Future Skate Park and Gazebo. Snack shack replacement Fencing (Basketball and ball fields) - use money in revolving or 10 fund Landscaping playground.
| Year | Funding
| FY2025 | 0
| FY2026 | 40000
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 11
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Gazebo
Department |  | Recreation
Project Type |  | Repair/Upgrade
Committee Assessment |  | No Recommendation
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 2500
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - No expenditures for 2026 Prior Year Notes: Add $2,500 to reserve for future repairs and maintenance.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 12
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Utility Building
Department |  | Cemetery
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - MAY have a 2026 project. MM will check with Trustees. Placeholder - Request budget info from cemetery committee. They have their own trust.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 13
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Elm Street Ball Park
Department |  | Recreation
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Long Term
Expenditure Year |  | 2027
Estimated Life |  | 25+ years
Estimated Cost |  | 100000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Pool/Rec Facilities
Estimated Inflation Rate |  | 5%
Project Description |  | Abby is requesting quotes for fencing project. Funding needs to be planned and will likely require some non-taxpayer money. Resizing of fields is due to be complete Fall 2025. Paid out of rec budget.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 14
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Basketball Court
Department |  | Recreation
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | Placeholder.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 15
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-26
Project Title |  | Tennis Court
Department |  | Recreation
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Pool/Rec Facilities
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - Cracking at base of net posts will need to be repaired. Ongoing maintenance/resurfacing.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 16
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2025-08-26
Project Title |  | Future Transfer Station - Full
Department |  | General Govt Buildings
Project Type |  | New
Committee Assessment |  | Recommend
Expenditure Year |  | 2026 | bulk of expenditure (see notes tab)
Estimated Life |  | 25+ years | updated (see notes tab) | 30
Estimated Cost |  | 1000000
Base Year |  | 2025
Likely Funding Source |  | State or Federal Grant
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | This option assumes a fully built transfer station using Aries Engineering design. - Congressional Discretionary Spending submitted by Senator Sheehan - EPA grant
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 1000000
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 17
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2025-08-26
Project Title |  | Future Public Safety Building
Department |  | Fire, EMS & Police | Fire, EMS & Police
Project Type |  | New
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2028 | Construction Year
Estimated Life |  | 25+ years
Estimated Cost |  | 5000000
Base Year |  | 2025
Likely Funding Source |  | Bond Issue
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 8/26/2025 - Engineering study is the next step - would come out of exisiting capital reserve. Very preliminary estimate. - No site selected - No engineering plans
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 18
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | Solar Array
Department |  | General Govt Buildings
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 Need warranty info from energy commission. 30 year life expectancy. Capital expenditures >$25k are unlikely. Maintenance (ballast failure) will be the first likely need at year 10. No need to make specific request to GGB this year.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 19
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | Prospect Street Building
Department |  | General Govt Buildings
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 Possible outdoor storage project in 2025 or 2026. See tab 4. Highway Department - needs new HVAC - - new boiler -- both are original to the building. Big Ass Fan (BAF) with a vent. Windows have been replaced.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 20
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | TA3500 - Trailer
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | No Planned Expenditure
Estimated Life |  | 25+ years
Estimated Cost |  | 2900 | current value
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Inactive
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - Storage for Fire Department in parking lot. Will likely get more use when FD gets utility truck. Unlikely that Town would replace this for $25k, delete or retire this tab.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 21
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2020 Explorer (Cruiser 2)
Department |  | Police
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2026
Estimated Life |  | 5 years or less | 100,000 miles is target useful life
Estimated Cost |  | 0
Base Year |  | 2029
Likely Funding Source |  | Reserve Fund
CRF Account |  | Police Cruiser
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - Replacement cycle is slowing because the Department has been understaffed (3 years). This replacement may shift to 2027. Mary will check with Chief. 9/28/2025 - This replacement may shift to 2027. Hybrid may need to be replaced before the 2019 it will depend on which is worse at the end of year. Ideally this will be replaced 2029 Annual request from $25,000 to $35,000.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 22
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2023 Charger (Cruiser 1)
Department |  | Police
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2029
Estimated Life |  | 5 years or less | 100,000 target useful life
Estimated Cost |  | 0
Base Year |  | 2029
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Police Cruiser
Estimated Inflation Rate |  | 5%
Project Description |  | See tabs 21 and 23. Life cycle is longer than patrol vehicles and will be the last to be replaced.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 23
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2019 Explorer (Cruiser 4)
Department |  | Police
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2027
Estimated Life |  | 5 years or less | target useful life is 100,000 miles
Estimated Cost |  | 0
Base Year |  | 2026
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Police Cruiser
Estimated Inflation Rate |  | 5%
Project Description |  | See tabs 21 and 23. Likely need to increase capital reserve or use unallocated fund balance and warrant article.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 24
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2025 Explorer (Cruiser 3)
Department |  | Police
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2031
Estimated Life |  | 5 years or less | 100,000 miles is target useful life
Estimated Cost |  | 70000
Base Year |  | 2031
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Police Cruiser
Estimated Inflation Rate |  | 5%
Project Description |  | See previous cruiser tabs
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 25
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2017 FT581 Trailer
Department |  | Police
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 3500 | current value
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Inactive
Estimated Inflation Rate |  | 5%
Project Description |  | Located at 116 site. Storage for police training materials. May be retired and reused at future transfer station. Not likely to be replaced. CONSIDER DELETING or RETIRING THIS TAB.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 26
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2020 M2 106 (Dump Truck John ) - 5 Ton
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2035
Estimated Life |  | 11-25 years
Estimated Cost |  | 300000
Base Year |  | 2035
Likely Funding Source |  | Reserve Fund
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 Continue adding to capital reserve $50k. This can also be replaced using revolving funds.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 27
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2024-10-08
Project Title |  | 2019 Ram 1500 Pickup (tradeable)
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2026
Estimated Life |  | 5 years or less
Estimated Cost |  | 70000
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | Possible move to transfer station.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 28
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2016 F350 - 1 Ton (from Water Dept.)
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 5 years or less
Estimated Cost |  | 100000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 This truck may or may not be replaced. FD got the last Water Department hand me down truck. 9/11/2025 Brett: Not a must have and if it is replaced it would be 5 years from now. It does get used but depending on circumstances will determine if it's replaced.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 29
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2018 Dump Truck - 5 Ton (Chris)
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2033
Estimated Life |  | 6-10 years
Estimated Cost |  | 300000
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 8/9/2025 - Need to look at large truck purchases coming up and compare to reserve and revolving fund.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 30
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2015 Loader 420 F2 IT (backhoe)
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2030
Estimated Life |  | 11-25 years
Estimated Cost |  | 101000 | current value est.
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - Review against capital plan and revolving fund.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 31
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2011 Dump Truck (Brett) - 5 Ton
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2026
Estimated Life |  | 25+ years
Estimated Cost |  | 300000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - This replacement year will probably push out a few.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 32
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2009 Dump Truck (Rick) - 5 Ton
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 11-25 years
Estimated Cost |  | 241041
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - Being replaced in 2025 - ordered and paid for (funded) 09/28/2025 submitting a grant opportunity to pay $250,000 of the $300,000. Truck is slated to be ready January 2026
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 33
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2024-10-08
Project Title |  | 1973 Grader
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | No Planned Expenditure
Estimated Life |  | 25+ years
Estimated Cost
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Inactive
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 Very expensive to replace. Currently grade 8 miles of road in Town. This will be dealt with when the inevitable happens. No need to plan for a replacement.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 34
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 1085D - Heavy Equipment
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2039
Estimated Life |  | 11-25 years
Estimated Cost |  | 300000
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - No need to plan for replacement at this time - - 2039 replacement year
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 35
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2023 Ram 5500 1 Ton
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2033
Estimated Life |  | 6-10 years
Estimated Cost |  | 100000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - Replacement is far in the future.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 36
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2020 926M (Loader)
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2035
Estimated Life |  | 11-25 years
Estimated Cost |  | 150000 | current value 135000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Highway Equipment
Estimated Inflation Rate |  | 5%
Project Description |  | 9/11/2025 12-15 year lifespan Brett explained rust drives replacement timing
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 37
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-08-05
Project Title |  | 2016 MSVII Ambulance
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2028
Estimated Life |  | 6-10 years
Estimated Cost |  | 400000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Ambulance
Estimated Inflation Rate |  | 5%
Project Description |  | $125,000 ambulance reserve 9/11/2025 Met with John and a new ambulance is going to cost roughly $400,000 and 2 years once ordered. Creating a revolving fund 2026 town meeting but will need to fund $250,000 possibily 4 years. 8/5/2025 - Reserve ask will be influenced by whether or not ambulance revolving fund is approved by taxpayers. Ambulance services generate $60k per year. Currently, this money goes into General Fund. Payrolls goes through General fund. Ask for $25k for reserve and project $35k to revolving fund in 2026.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 38
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2004 Fire Truck
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | No Planned Expenditure
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Inactive
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 - This truck will be SOLD. Capital Reserve and ARPA funds. Replacemet is on back order. Fully funded! 9/11/2025 John is working on selling this trck and proceeds should go to the capital reserve
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 39
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 2000 FL-80 - Pumper
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2027
Estimated Life |  | 25+ years
Estimated Cost |  | 1000000
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Fire Truck
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 24 year old truck. We have 1 brand new truck coming in 2025. May or may not need to be replaced when it fails. Remaining life is short. Replacement if it happens will need to be paid for with a bond issue. Insurance upto 20 years covers the actual truck after 20 yrs it's the value of the truck 8/5/2025 - Fire Chief believes that truck should be replaced. Timing TBD.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 40
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 1998 Tanker
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2034
Estimated Life |  | 25+ years
Estimated Cost |  | 500000 | $100,000 is current value
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Fire Truck
Estimated Inflation Rate |  | 5%
Project Description |  | 9/9/2025 May be an opportunity to fund with grants.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 41
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 1977 F150 Brush Truck
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | No Planned Expenditure
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Inactive
Estimated Inflation Rate |  | 5%
Project Description |  | Not going to be replaced. RETIRE THIS TAB
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 42
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2025-09-09
Project Title |  | 1948 Fire Truck
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | No Planned Expenditure
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Inactive
Estimated Inflation Rate |  | 5%
Project Description |  | Not being replaced. RETIRE THIS TAB
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 43
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2024-08-20
Project Title |  | 2025 New Fire Truck
Department |  | Fire & Rescue
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2045
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | Replacement for the other truck.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 44
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-08-20
Last Edited |  | 2024-08-20
Project Title |  | Prospect Street Bridge
Department |  | Highway
Project Type |  | Replacement
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Budget or Warrant Article
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | Placeholder.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 45
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2024-09-03
Project Title |  | Future Transfer Station - Full (bond)
Department |  | General Govt Buildings
Project Type |  | New
Committee Assessment |  | Recommend
Expenditure Year |  | 2026 | bulk of expenditure
Estimated Life |  | 25+ years
Estimated Cost |  | 750000
Base Year |  | 2025
Likely Funding Source |  | Bond Issue
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | This option assumes a fully built transfer station using Aries Engineering design. Difference is that Town would use existing capital reserve, minor grants and then borrow the remaining balance.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 46
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2024-09-03
Project Title |  | Future Transfer Station - Phase 1
Department |  | General Govt Buildings
Project Type |  | New
Committee Assessment |  | Recommend
Expenditure Year |  | 2026 | bulk of expenditure
Estimated Life |  | 25+ years
Estimated Cost |  | 300000
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | Phase 1 using only Town resources (capital reserve fund, minor local grants).
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 47
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2024-09-03
Last Edited |  | 2025-09-09
Project Title |  | Town Hall - Other upgrades and repairs
Department |  | General Govt Buildings
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years | 20
Estimated Cost |  | 0 | need to research
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | Front Door replaced, double hung windows replaced or repaired, non-functioning interior doors, re-point mortar. Some of appropriation could come out of general building maintenance line item.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0

## 48
CAPITAL IMPROVEMENT PROJECT SHEET
Date Added |  | 2025-08-26
Last Edited |  | 2025-08-26
Project Title |  | Major Road Projects
Department |  | Highway
Project Type |  | Repair/Upgrade
Committee Assessment |  | Defer Short Term
Expenditure Year |  | 2025
Estimated Life |  | 25+ years
Estimated Cost |  | 0
Base Year |  | 2025
Likely Funding Source |  | Reserve Fund
CRF Account |  | Town Building Maintenance
Estimated Inflation Rate |  | 5%
Project Description |  | 8/29/2025 - Need to consider adding money to highway maintenance capital reserve.
| Year | Funding
| FY2025 | 0
| FY2026 | 0
| FY2027 | 0
| FY2028 | 0
| FY2029 | 0
| FY2030 | 0